## Timeline
Start Date | Hours of per week | Estimated Date of Completion
Enter the date you started studying | Enter the number you will commit | Lower Bound | Upper Bound
2024-12-16 | 20 | 2026-07-26 15:36 | 2027-03-19 04:48

## Curriculum Data
No. | Courses | Topic | Duration (weeks) | Effort (hours/week) |  | Total Hours Lower Bound | Start Date | End Date Estimate Lower Bound | Total Hours Upper Bound | Start Date | End Date Estimate Upper Bound | Actual End Date | Prerequisites | Effort note | Note | Alternative
|  |  |  | Lower bound | Upper bound
1 | Introduction to Computer Science and Programming using Python | Intro CS | 9 | 15 | 15 | 135 | 2024-12-16 | 2025-02-01 06:00 | 135 | 2024-12-16 | 2025-02-01 06:00 |  | high school algebra
2 | Systematic Program Design | Core Programming | 13 | 8 | 10 | 104 | 2025-02-01 06:00 | 2025-03-09 15:36 | 130 | 2025-02-01 06:00 | 2025-03-18 18:00 |  | -
3 | Class-based Program Design | Core Programming | 13 | 5 | 10 | 65 | 2025-03-09 15:36 | 2025-04-01 09:36 | 130 | 2025-03-18 18:00 | 2025-05-03 06:00 |  | Systematic Program Design, High School Math
4 | Programming Languages, Part A | Core Programming | 5 | 4 | 8 | 20 | 2025-04-01 09:36 | 2025-04-08 09:36 | 40 | 2025-05-03 06:00 | 2025-05-17 06:00 |  | How to Code (Hear instructor)
5 | Programming Languages, Part B | Core Programming | 3 | 4 | 8 | 12 | 2025-04-08 09:36 | 2025-04-12 14:24 | 24 | 2025-05-17 06:00 | 2025-05-25 15:36 |  | Programming Languages, Part A
6 | Programming Languages, Part C | Core Programming | 3 | 4 | 8 | 12 | 2025-04-12 14:24 | 2025-04-16 19:12 | 24 | 2025-05-25 15:36 | 2025-06-03 01:12 |  | Programming Languages, Part B
7 | Object-Oriented Design | Core Programming | 13 | 5 | 10 | 65 | 2025-04-16 19:12 | 2025-05-09 13:12 | 130 | 2025-06-03 01:12 | 2025-07-18 13:12 |  | Class-based Program Design
8 | Software Architecture | Core Programming | 4 | 2 | 5 | 8 | 2025-05-09 13:12 | 2025-05-12 08:24 | 20 | 2025-07-18 13:12 | 2025-07-25 13:12 |  | Object-Oriented Design
9 | Calculus 1A: Differentiation | Core Math | 13 | 6 | 10 | 78 | 2025-05-12 08:24 | 2025-06-08 15:36 | 130 | 2025-07-25 13:12 | 2025-09-09 01:12 |  | high school math
10 | Calculus 1B: Integration | Core Math | 13 | 5 | 10 | 65 | 2025-06-08 15:36 | 2025-07-01 09:36 | 130 | 2025-09-09 01:12 | 2025-10-24 13:12 |  | Calculus 1A
11 | Calculus 1C: Coordinate Systems & Infinite Series | Core Math | 6 | 5 | 10 | 30 | 2025-07-01 09:36 | 2025-07-11 21:36 | 60 | 2025-10-24 13:12 | 2025-11-14 13:12 |  | Calculus 1B
12 | Mathematics for Computer Science | Core Math | 13 | 5 | 5 | 65 | 2025-07-11 21:36 | 2025-08-03 15:36 | 65 | 2025-11-14 13:12 | 2025-12-07 07:12 |  | Calculus 1C
13 | The Missing Semester of Your CS Education | CS Tools | 2 | 12 | 12 | 24 | 2025-08-03 15:36 | 2025-08-12 01:12 | 24 | 2025-12-07 07:12 | 2025-12-15 16:48 |  | -
14 | Build a Modern Computer from First Principles: From Nand to Tetris | Core Systems | 6 | 7 | 13 | 42 | 2025-08-12 01:12 | 2025-08-26 18:00 | 78 | 2025-12-15 16:48 | 2026-01-12 |  | C-like programming language
15 | Build a Modern Computer from First Principles: Nand to Tetris Part II | Core Systems | 6 | 12 | 18 | 72 | 2025-08-26 18:00 | 2025-09-20 22:48 | 108 | 2026-01-12 | 2026-02-18 19:12 |  | Nand to Tetris Part I
16 | Operating Systems: Three Easy Pieces | Core Systems | 12 | 5 | 10 | 60 | 2025-09-20 22:48 | 2025-10-11 22:48 | 120 | 2026-02-18 19:12 | 2026-04-01 19:12 |  | Nand to Tetris Part II
17 | Computer Networking: a Top-Down Approach | Core Systems | 8 | 4 | 12 | 32 | 2025-10-11 22:48 | 2025-10-23 03:36 | 96 | 2026-04-01 19:12 | 2026-05-05 09:36 |  | algebra, probability, basic CS
18 | Divide and Conquer, Sorting and Searching, and Randomized Algorithms | Core Theory | 4 | 4 | 8 | 16 | 2025-10-23 03:36 | 2025-10-28 18:00 | 32 | 2026-05-05 09:36 | 2026-05-16 14:24 |  | any programming language, Mathematics for Computer Science
19 | Graph Search, Shortest Paths, and Data Structures | Core Theory | 4 | 4 | 8 | 16 | 2025-10-28 18:00 | 2025-11-03 08:24 | 32 | 2026-05-16 14:24 | 2026-05-27 19:12 |  | Divide and Conquer, Sorting and Searching, and Randomized Algorithms
20 | Greedy Algorithms, Minimum Spanning Trees, and Dynamic Programming | Core Theory | 4 | 4 | 8 | 16 | 2025-11-03 08:24 | 2025-11-08 22:48 | 32 | 2026-05-27 19:12 | 2026-06-08 |  | Graph Search, Shortest Paths, and Data Structures
21 | Shortest Paths Revisited, NP-Complete Problems and What To Do About Them | Core Theory | 4 | 4 | 8 | 16 | 2025-11-08 22:48 | 2025-11-14 13:12 | 32 | 2026-06-08 | 2026-06-19 04:48 |  | Greedy Algorithms, Minimum Spanning Trees, and Dynamic Programming
22 | Cybersecurity Fundamentals | Core Security | 8 | 10 | 12 | 80 | 2025-11-14 13:12 | 2025-12-12 13:12 | 96 | 2026-06-19 04:48 | 2026-07-22 19:12 |  | -
23 | Principles of Secure Coding | Core Security | 4 | 4 | 4 | 16 | 2025-12-12 13:12 | 2025-12-18 03:36 | 16 | 2026-07-22 19:12 | 2026-07-28 09:36 |  | -
24 | Identifying Security Vulnerabilities | Core Security | 4 | 4 | 4 | 16 | 2025-12-18 03:36 | 2025-12-23 18:00 | 16 | 2026-07-28 09:36 | 2026-08-03 |  | -
25 | Identifying Security Vulnerabilities in C/C++ Programming | Core Security | 4 | 5 | 5 | 20 | 2025-12-23 18:00 | 2025-12-30 18:00 | 20 | 2026-08-03 | 2026-08-10 |  | - |  |  | Choose one of either item 27 or 28. Default: 27
26 | Exploiting and Securing Vulnerabilities in Java Applications | Core Security | 4 | 0 | 0 | 0 | 2025-12-30 18:00 | 2025-12-30 18:00 | 0 | 2026-08-10 | 2026-08-10 |  |  | 5
27 | Databases: Modeling and Theory | Core Applications | 2 | 10 | 10 | 20 | 2025-12-30 18:00 | 2026-01-06 18:00 | 20 | 2026-08-10 | 2026-08-17 |  | core programming
28 | Databases: Relational Databases and SQL | Core Applications | 2 | 10 | 10 | 20 | 2026-01-06 18:00 | 2026-01-13 18:00 | 20 | 2026-08-17 | 2026-08-24 |  | core programming
29 | Databases: Semistructured Data | Core Applications | 2 | 10 | 10 | 20 | 2026-01-13 18:00 | 2026-01-20 18:00 | 20 | 2026-08-24 | 2026-08-31 |  | core programming
30 | Machine Learning | Core Applications | 11 | 9 | 9 | 99 | 2026-01-20 18:00 | 2026-02-24 09:36 | 99 | 2026-08-31 | 2026-10-04 15:36 |  | linear algebra
31 | Computer Graphics | Core Applications | 6 | 12 | 12 | 72 | 2026-02-24 09:36 | 2026-03-21 14:24 | 72 | 2026-10-04 15:36 | 2026-10-29 20:24 |  | C++ or Java, linear algebra
32 | Software Engineering: Introduction | Core Applications | 6 | 8 | 10 | 48 | 2026-03-21 14:24 | 2026-04-07 09:36 | 60 | 2026-10-29 20:24 | 2026-11-19 20:24 |  | Core Programming, and a sizable project
33 | Ethics, Technology and Engineering | Core Ethics | 9 | 2 | 2 | 18 | 2026-04-07 09:36 | 2026-04-13 16:48 | 18 | 2026-11-19 20:24 | 2026-11-26 03:36 |  | -
34 | Introduction to Intellectual Property | Core Ethics | 4 | 2 | 2 | 8 | 2026-04-13 16:48 | 2026-04-16 12:00 | 8 | 2026-11-26 03:36 | 2026-11-28 22:48 |  | -
35 | Data Privacy Fundamentals | Core Ethics | 3 | 3 | 3 | 9 | 2026-04-16 12:00 | 2026-04-19 15:36 | 9 | 2026-11-28 22:48 | 2026-12-02 02:24 |  | -
36 | Parallel Programming | Advanced Programming | 4 | 6 | 8 | 24 | 2026-04-19 15:36 | 2026-04-28 01:12 | 32 | 2026-12-02 02:24 | 2026-12-13 07:12 |  | Scala programming | 6 - 8 | Effort 6 - 8h | Can choose 1 track for advanced CS. Default: Programming
37 | Compilers | Advanced Programming | 9 | 6 | 8 | 54 | 2026-04-28 01:12 | 2026-05-16 22:48 | 72 | 2026-12-13 07:12 | 2027-01-07 12:00 |  | none | 6 - 8 | Effort 6 - 8h
38 | Introduction to Haskell | Advanced Programming | 14 | 5 | 5 | 70 | 2026-05-16 22:48 | 2026-06-10 10:48 | 70 | 2027-01-07 12:00 | 2027-02-01 |  | - | estimate 5 | No recommended effort
39 | Learn Prolog Now! | Advanced Programming | 12 | 5 | 5 | 60 | 2026-06-10 10:48 | 2026-07-01 10:48 | 60 | 2027-02-01 | 2027-02-22 |  | - | estimate 5 | No recommended effort
40 | Software Debugging | Advanced Programming | 8 | 6 | 6 | 48 | 2026-07-01 10:48 | 2026-07-18 06:00 | 48 | 2027-02-22 | 2027-03-10 19:12 |  | Python, object-oriented programming | 6 | Youtube alternative link is available. | https://www.youtube.com/playlist?list=PLAwxTw4SYaPkxK63TiT88oEe-AIBhr96A
41 | Software Testing | Advanced Programming | 4 | 6 | 6 | 24 | 2026-07-18 06:00 | 2026-07-26 15:36 | 24 | 2027-03-10 19:12 | 2027-03-19 04:48 |  | Python, programming experience | 6 | Youtube alternative link is available. | https://www.youtube.com/playlist?list=PLAwxTw4SYaPkWVHeC_8aSIbSxE_NXI76g
42 | Computation Structures 1: Digital Circuits | Advanced Systems | 4 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Nand to tetris II | 6 | Alternative link for all 3 courses. | https://ocw.mit.edu/courses/6-004-computation-structures-spring-2017/
43 | Computation Structures 2: Computer Architecture | Advanced Systems | 4 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Computation Structures 1: Digital Circuits | 6
44 | Computation Structures 3: Computer Organization | Advanced Systems | 4 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Computation Structures 2: Computer Architecture | 6
45 | Theory of Computation | Advanced Theory | 13 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Mathematics for Computer Science, Logic, Algorithms | 10
46 | Computational Geometry | Advanced Theory | 16 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Algorithms, C++ | 8
47 | Game Theory | Advanced Theory | 8 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Mathematical thinking, probability, calculus | 3
48 | Web Security Fundamentals | Advanced Information Security | 5 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Understanding basic web technologies | 4 - 6
49 | Security Governance & Compliance | Advanced Information Security | 3 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | - | 3
50 | Digital Forensics Concepts | Advanced Information Security | 3 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Core Security | 2 - 3
51 | Secure Software Development: Requirements, Design, and Reuse | Advanced Information Security | 7 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Core Programming and Core Security | 1 - 2
52 | Secure Software Development: Implementation | Advanced Information Security | 7 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Secure Software Development: Requirements, Design, and Reuse | 1 - 2
53 | Secure Software Development: Verification and More Specialized Topics | Advanced Information Security | 7 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Secure Software Development: Implementation | 1 - 2
54 | Essence of Linear Algebra | Advanced Math | 5 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | high school math | 4
55 | Linear Algebra | Advanced Math | 14 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Essence of Linear Algebra | 12
56 | Introduction to Numerical Methods | Advanced Math | 14 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Linear Algebra | 12
57 | Introduction to Formal Logic | Advanced Math | 10 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Set Theory | 4 - 8
58 | Probability | Advanced Math | 15 | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48 |  | Core Math | 5 - 10
59 | Final Project | Final Project |  | 0 | 0 | 0 | 2026-07-26 15:36 | 2026-07-26 15:36 | 0 | 2027-03-19 04:48 | 2027-03-19 04:48
Formulas:
Start Date = IF(ISBLANK([Actual End Date, row above]),[End Date Estimate Lower Bound, row above],[Actual End Date, row above])
Start Date = IF(ISBLANK([Actual End Date, row above]),[End Date Estimate Upper Bound, row above],[Actual End Date, row above])
End Date Estimate Lower Bound = IF(ISBLANK([Actual End Date]),[Start Date]+([Total Hours Lower Bound]/(Timeline!$B3/7)),[Actual End Date])
End Date Estimate Upper Bound = IF(ISBLANK([Actual End Date]),[Start Date]+([Total Hours Upper Bound]/(Timeline!$B3/7)),[Actual End Date])